## Mamba_MVP_Official_Syllabus_Sch
Date | Day | Week | Sprint Phase | Module / Tactical Focus | Exercise / Activity | Owner / Lead | Weekly Deliverable / Milestone | TAKSHMA | MATTHEW
2026-10-05 | Mon | WK 01 | Sprint 1: Problem, Founder Thesis & Opportunity | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-10-06 | Tue | WK 01 | Sprint 1: Problem, Founder Thesis & Opportunity | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-10-07 | Wed | WK 01 | Sprint 1: Problem, Founder Thesis & Opportunity | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-10-08 | Thu | WK 01 | Sprint 1: Problem, Founder Thesis & Opportunity | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-10-09 | Fri | WK 01 | Sprint 1: Problem, Founder Thesis & Opportunity | Deliverable Push & Weekly Dashboard Update | Analytics, demo prep & updating KPI progress dashboard | Founders | 1-page venture thesis & Top 10 assumptions ranked
2026-10-12 | Mon | WK 02 | Sprint 1: Ideation, Concept Selection & Sprint 1 Review | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-10-13 | Tue | WK 02 | Sprint 1: Ideation, Concept Selection & Sprint 1 Review | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-10-14 | Wed | WK 02 | Sprint 1: Ideation, Concept Selection & Sprint 1 Review | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-10-15 | Thu | WK 02 | Sprint 1: Ideation, Concept Selection & Sprint 1 Review | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-10-16 | Fri | WK 02 | Sprint 1: Ideation, Concept Selection & Sprint 1 Review | Sprint Gate & Evidence Review | 60-90 min Formal Review: KPIs, Evidence Pack & Go/Iterate/Pivot Decision | Founders | Selected concept, Value prop & Sprint 1 evidence pack
2026-10-19 | Mon | WK 03 | Sprint 2: Product Verification & Customer Discovery | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-10-20 | Tue | WK 03 | Sprint 2: Product Verification & Customer Discovery | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-10-21 | Wed | WK 03 | Sprint 2: Product Verification & Customer Discovery | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-10-22 | Thu | WK 03 | Sprint 2: Product Verification & Customer Discovery | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-10-23 | Fri | WK 03 | Sprint 2: Product Verification & Customer Discovery | Deliverable Push & Weekly Dashboard Update | Analytics, demo prep & updating KPI progress dashboard | Founders | Interview insight repo & Problem evidence scorecard
2026-10-26 | Mon | WK 04 | Sprint 2: Market Research, Competition & Sprint 2 Review | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-10-27 | Tue | WK 04 | Sprint 2: Market Research, Competition & Sprint 2 Review | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-10-28 | Wed | WK 04 | Sprint 2: Market Research, Competition & Sprint 2 Review | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-10-29 | Thu | WK 04 | Sprint 2: Market Research, Competition & Sprint 2 Review | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-10-30 | Fri | WK 04 | Sprint 2: Market Research, Competition & Sprint 2 Review | Sprint Gate & Evidence Review | 60-90 min Formal Review: KPIs, Evidence Pack & Go/Iterate/Pivot Decision | Founders | Market landscape, Competitor matrix & Sprint 2 decision
2026-11-02 | Mon | WK 05 | Sprint 3: ICP, Segmentation & Buying Motion | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-11-03 | Tue | WK 05 | Sprint 3: ICP, Segmentation & Buying Motion | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-11-04 | Wed | WK 05 | Sprint 3: ICP, Segmentation & Buying Motion | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-11-05 | Thu | WK 05 | Sprint 3: ICP, Segmentation & Buying Motion | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-11-06 | Fri | WK 05 | Sprint 3: ICP, Segmentation & Buying Motion | Deliverable Push & Weekly Dashboard Update | Analytics, demo prep & updating KPI progress dashboard | Founders | Primary/Secondary ICP cards & Top 50-100 target accounts
2026-11-09 | Mon | WK 06 | Sprint 3: Pricing, Unit Economics & Sprint 3 Review | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-11-10 | Tue | WK 06 | Sprint 3: Pricing, Unit Economics & Sprint 3 Review | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-11-11 | Wed | WK 06 | Sprint 3: Pricing, Unit Economics & Sprint 3 Review | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-11-12 | Thu | WK 06 | Sprint 3: Pricing, Unit Economics & Sprint 3 Review | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-11-13 | Fri | WK 06 | Sprint 3: Pricing, Unit Economics & Sprint 3 Review | Sprint Gate & Evidence Review | 60-90 min Formal Review: KPIs, Evidence Pack & Go/Iterate/Pivot Decision | Founders | Pricing v1, Basic unit economics & Sprint 3 commercial thesis
2026-11-16 | Mon | WK 07 | Sprint 4: GTM Strategy & Demand Generation | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-11-17 | Tue | WK 07 | Sprint 4: GTM Strategy & Demand Generation | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-11-18 | Wed | WK 07 | Sprint 4: GTM Strategy & Demand Generation | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-11-19 | Thu | WK 07 | Sprint 4: GTM Strategy & Demand Generation | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-11-20 | Fri | WK 07 | Sprint 4: GTM Strategy & Demand Generation | Deliverable Push & Weekly Dashboard Update | Analytics, demo prep & updating KPI progress dashboard | Founders | GTM one-pager, Messaging framework & Initial pipeline
2026-11-23 | Mon | WK 08 | Sprint 4: MVP Scope, Engineering & Sprint 4 Review | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-11-24 | Tue | WK 08 | Sprint 4: MVP Scope, Engineering & Sprint 4 Review | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-11-25 | Wed | WK 08 | Sprint 4: MVP Scope, Engineering & Sprint 4 Review | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-11-26 | Thu | WK 08 | Sprint 4: MVP Scope, Engineering & Sprint 4 Review | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-11-27 | Fri | WK 08 | Sprint 4: MVP Scope, Engineering & Sprint 4 Review | Sprint Gate & Evidence Review | 60-90 min Formal Review: KPIs, Evidence Pack & Go/Iterate/Pivot Decision | Founders | Prioritized PRD, Tech roadmap & Sprint 4 build-readiness gate
2026-11-30 | Mon | WK 09 | Sprint 5: MVP Build Sprint I | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-12-01 | Tue | WK 09 | Sprint 5: MVP Build Sprint I | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-12-02 | Wed | WK 09 | Sprint 5: MVP Build Sprint I | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-12-03 | Thu | WK 09 | Sprint 5: MVP Build Sprint I | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-12-04 | Fri | WK 09 | Sprint 5: MVP Build Sprint I | Deliverable Push & Weekly Dashboard Update | Analytics, demo prep & updating KPI progress dashboard | Founders | Functional core journey, Weekly demo & Bug backlog
2026-12-07 | Mon | WK 10 | Sprint 5: MVP Build Sprint II & Market Readiness | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-12-08 | Tue | WK 10 | Sprint 5: MVP Build Sprint II & Market Readiness | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-12-09 | Wed | WK 10 | Sprint 5: MVP Build Sprint II & Market Readiness | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-12-10 | Thu | WK 10 | Sprint 5: MVP Build Sprint II & Market Readiness | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-12-11 | Fri | WK 10 | Sprint 5: MVP Build Sprint II & Market Readiness | Sprint Gate & Evidence Review | 60-90 min Formal Review: KPIs, Evidence Pack & Go/Iterate/Pivot Decision | Founders | Release candidate (Beta v1), Launch assets ready & Sprint 5 Review
2026-12-14 | Mon | WK 11 | Sprint 6: Soft Launch & Live Validation | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-12-15 | Tue | WK 11 | Sprint 6: Soft Launch & Live Validation | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-12-16 | Wed | WK 11 | Sprint 6: Soft Launch & Live Validation | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-12-17 | Thu | WK 11 | Sprint 6: Soft Launch & Live Validation | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-12-18 | Fri | WK 11 | Sprint 6: Soft Launch & Live Validation | Deliverable Push & Weekly Dashboard Update | Analytics, demo prep & updating KPI progress dashboard | Founders | First live users, Launch KPI baseline & Top 5 iteration priorities
2026-12-21 | Mon | WK 12 | Sprint 6: Iterate, Demo & 90-Day Scale Plan / Sprint 6 Review | Sprint Planning & Deep Work Setup | 4-6 hrs build time + 45 min Mentor/Advisor Sync (Decisions/Accountability) | Founders / Mentor
2026-12-22 | Tue | WK 12 | Sprint 6: Iterate, Demo & 90-Day Scale Plan / Sprint 6 Review | Protected Build & Functional Execution | 5-7 hrs deep work + 45 min Functional Specialist (Product/Eng/GTM) | Founders / Functional Lead
2026-12-23 | Wed | WK 12 | Sprint 6: Iterate, Demo & 90-Day Scale Plan / Sprint 6 Review | Program Lead Office Hours (The Anchor) | 1 hr Office Hours: Dashboard review, block removal & decision locking | Mamba Program Lead
2026-12-24 | Thu | WK 12 | Sprint 6: Iterate, Demo & 90-Day Scale Plan / Sprint 6 Review | Validation, Testing & Industry Alignment | 5-7 hrs build time + 45 min Industry Specialist (Domain/Customer) | Founders / Industry Lead
2026-12-25 | Fri | WK 12 | Sprint 6: Iterate, Demo & 90-Day Scale Plan / Sprint 6 Review | Batch Closed | Christmas Public Holiday (Demo Day & Final Review completed earlier in week) | Founders | MVP Demo, 90-day operating plan & Decision: Iterate/Scale/Pivot

## Cybrdeck_Syllabus_Schedule
Date | Day | Week | Sprint Phase | Module / Tactical Focus | Exercise / Activity | Owner / Lead | Weekly Deliverable / Milestone | TAKSHMA | MATTHEW
2026-10-05 | Mon | WK 01 | Sprint 1: Technical Feasibility & Architecture Setup | Sprint Planning & Architecture Setup | 4-6 hrs build time + Architecture Setup: Evaluate feasibility against APIs/LLMs/time. | Founders / Cybrdeck Lead
2026-10-06 | Tue | WK 01 | Sprint 1: Technical Feasibility & Architecture Setup | Protected Build & Engineering Execution | 5-7 hrs deep work: Evaluate technical stack feasibility & latency tradeoffs. | Founders / Cybrdeck Lead
2026-10-07 | Wed | WK 01 | Sprint 1: Technical Feasibility & Architecture Setup | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Feasibility & API constraints. | Mamba Program Lead
2026-10-08 | Thu | WK 01 | Sprint 1: Technical Feasibility & Architecture Setup | Validation, Testing & Integrations | 5-7 hrs build time: Prototype core LLM calls, token limits & latency benchmarking. | Founders / Cybrdeck Lead
2026-10-09 | Fri | WK 01 | Sprint 1: Technical Feasibility & Architecture Setup | Deliverable Push & Weekly Codebase Review | Weekly review & push: Synthesize feasibility findings & technical roadmap. | Founders / Cybrdeck Lead
2026-10-12 | Mon | WK 02 | Sprint 1: Technical Scoping & SOW Finalization | Sprint Planning & Architecture Setup | 4-6 hrs build time + Sprint Planning: Define Cybrdeck build vs Wizard of Oz manual testing. | Founders / Cybrdeck Lead
2026-10-13 | Tue | WK 02 | Sprint 1: Technical Scoping & SOW Finalization | Protected Build & Engineering Execution | 5-7 hrs deep work: Map manual workflows against MVP automated components. | Founders / Cybrdeck Lead
2026-10-14 | Wed | WK 02 | Sprint 1: Technical Scoping & SOW Finalization | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Lock MVP scope & boundary definitions. | Mamba Program Lead
2026-10-15 | Thu | WK 02 | Sprint 1: Technical Scoping & SOW Finalization | Validation, Testing & Integrations | 5-7 hrs build time: Draft technical architecture specifications & dependency matrix. | Founders / Cybrdeck Lead
2026-10-16 | Fri | WK 02 | Sprint 1: Technical Scoping & SOW Finalization | Deliverable Push & Weekly Codebase Review | 60-90 min Technical Gate: Finalize and sign Technical SOW. | Founders / Cybrdeck Lead | Signed Technical SOW
2026-10-19 | Mon | WK 03 | Sprint 2: Data Architecture & Schema Design | Sprint Planning & Architecture Setup | 4-6 hrs build time + Architecture Setup: Map data flow, design database schema (Supabase/Postgres). | Founders / Cybrdeck Lead
2026-10-20 | Tue | WK 03 | Sprint 2: Data Architecture & Schema Design | Protected Build & Engineering Execution | 5-7 hrs deep work: Construct relational entities, foreign keys & indexes in Supabase. | Founders / Cybrdeck Lead
2026-10-21 | Wed | WK 03 | Sprint 2: Data Architecture & Schema Design | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Validate schema normalization & security rules. | Mamba Program Lead
2026-10-22 | Thu | WK 03 | Sprint 2: Data Architecture & Schema Design | Validation, Testing & Integrations | 5-7 hrs build time: Configure migration scripts & test synthetic data seeders. | Founders / Cybrdeck Lead
2026-10-23 | Fri | WK 03 | Sprint 2: Data Architecture & Schema Design | Deliverable Push & Weekly Codebase Review | Weekly codebase review & push: Audit database schema and data models. | Founders / Cybrdeck Lead
2026-10-26 | Mon | WK 04 | Sprint 2: Staging Environments & Sandbox Setup | Sprint Planning & Architecture Setup | 4-6 hrs build time + Architecture Setup: Spin up staging environments (VPC) and GitHub repos. | Founders / Cybrdeck Lead
2026-10-27 | Tue | WK 04 | Sprint 2: Staging Environments & Sandbox Setup | Protected Build & Engineering Execution | 5-7 hrs deep work: Configure CI/CD deployment pipelines & branch protection rules. | Founders / Cybrdeck Lead
2026-10-28 | Wed | WK 04 | Sprint 2: Staging Environments & Sandbox Setup | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Resolve VPC networking & deployment secrets. | Mamba Program Lead
2026-10-29 | Thu | WK 04 | Sprint 2: Staging Environments & Sandbox Setup | Validation, Testing & Integrations | 5-7 hrs build time: Test multi-tenant isolation & staging deployment pipelines. | Founders / Cybrdeck Lead
2026-10-30 | Fri | WK 04 | Sprint 2: Staging Environments & Sandbox Setup | Deliverable Push & Weekly Codebase Review | 60-90 min Sandbox Review: Validate live DB schema and developer sandbox. | Founders / Cybrdeck Lead | Live DB schema, developer sandbox
2026-11-02 | Mon | WK 05 | Sprint 3: User Authentication & Session Security | Sprint Planning & Architecture Setup | 4-6 hrs build time + Architecture Setup: Deploy user login, secure routing, session management. | Founders / Cybrdeck Lead
2026-11-03 | Tue | WK 05 | Sprint 3: User Authentication & Session Security | Protected Build & Engineering Execution | 5-7 hrs deep work: Implement JWT authentication, token refresh & RBAC middleware. | Founders / Cybrdeck Lead
2026-11-04 | Wed | WK 05 | Sprint 3: User Authentication & Session Security | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Debug auth session lifecycle & redirect flows. | Mamba Program Lead
2026-11-05 | Thu | WK 05 | Sprint 3: User Authentication & Session Security | Validation, Testing & Integrations | 5-7 hrs build time: Test authentication guards, cookie policies & CSRF protection. | Founders / Cybrdeck Lead
2026-11-06 | Fri | WK 05 | Sprint 3: User Authentication & Session Security | Deliverable Push & Weekly Codebase Review | Weekly codebase review & push: Validate end-to-end user login and secure routing. | Founders / Cybrdeck Lead
2026-11-09 | Mon | WK 06 | Sprint 3: Third-Party Integrations & API Connections | Sprint Planning & Architecture Setup | 4-6 hrs build time + Architecture Setup: Connect third-party services (Claude/OpenAI, Stripe, webhooks). | Founders / Cybrdeck Lead
2026-11-10 | Tue | WK 06 | Sprint 3: Third-Party Integrations & API Connections | Protected Build & Engineering Execution | 5-7 hrs deep work: Build API clients, rate limit handling & exponential retry logic. | Founders / Cybrdeck Lead
2026-11-11 | Wed | WK 06 | Sprint 3: Third-Party Integrations & API Connections | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Verify webhook signature validation & async events. | Mamba Program Lead
2026-11-12 | Thu | WK 06 | Sprint 3: Third-Party Integrations & API Connections | Validation, Testing & Integrations | 5-7 hrs build time: Test mock payment events, LLM streaming & provider fallbacks. | Founders / Cybrdeck Lead
2026-11-13 | Fri | WK 06 | Sprint 3: Third-Party Integrations & API Connections | Deliverable Push & Weekly Codebase Review | 60-90 min Review & Demo: Showcase authenticated staging app with live APIs. | Founders / Cybrdeck Lead | Authenticated staging app with APIs
2026-11-16 | Mon | WK 07 | Sprint 4: Core Logic & Prompt Chaining Architecture | Sprint Planning & Architecture Setup | 4-6 hrs build time + Architecture Setup: Build core CRUD and prompt-chaining logic. | Founders / Cybrdeck Lead
2026-11-17 | Tue | WK 07 | Sprint 4: Core Logic & Prompt Chaining Architecture | Protected Build & Engineering Execution | 5-7 hrs deep work: Implement sequential prompt pipelines & context window managers. | Founders / Cybrdeck Lead
2026-11-18 | Wed | WK 07 | Sprint 4: Core Logic & Prompt Chaining Architecture | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Optimize prompt token usage & error handling. | Mamba Program Lead
2026-11-19 | Thu | WK 07 | Sprint 4: Core Logic & Prompt Chaining Architecture | Validation, Testing & Integrations | 5-7 hrs build time: Enforce structured JSON schemas & output validation parser. | Founders / Cybrdeck Lead
2026-11-20 | Fri | WK 07 | Sprint 4: Core Logic & Prompt Chaining Architecture | Deliverable Push & Weekly Codebase Review | Weekly codebase review & push: Benchmark prompt execution latency & verify CRUD endpoints. | Founders / Cybrdeck Lead
2026-11-23 | Mon | WK 08 | Sprint 4: Backend API Stitching & Endpoint Finalization | Sprint Planning & Architecture Setup | 4-6 hrs build time + Architecture Setup: Stitch backend APIs to use case requirements. | Founders / Cybrdeck Lead
2026-11-24 | Tue | WK 08 | Sprint 4: Backend API Stitching & Endpoint Finalization | Protected Build & Engineering Execution | 5-7 hrs deep work: Wire REST/tRPC handlers to database queries & prompt workflows. | Founders / Cybrdeck Lead
2026-11-25 | Wed | WK 08 | Sprint 4: Backend API Stitching & Endpoint Finalization | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Resolve payload serialization & concurrency issues. | Mamba Program Lead
2026-11-26 | Thu | WK 08 | Sprint 4: Backend API Stitching & Endpoint Finalization | Validation, Testing & Integrations | 5-7 hrs build time: Run end-to-end endpoint load tests & API contract tests. | Founders / Cybrdeck Lead
2026-11-27 | Fri | WK 08 | Sprint 4: Backend API Stitching & Endpoint Finalization | Deliverable Push & Weekly Codebase Review | 60-90 min Codebase Review: Confirm functional backend endpoints and API docs. | Founders / Cybrdeck Lead | Functional backend endpoints
2026-11-30 | Mon | WK 09 | Sprint 5: Front-End UI Integration & Vercel Deployment | Sprint Planning & Architecture Setup | 4-6 hrs build time + Architecture Setup: Connect backend logic to UI (Vercel/Next.js). | Founders / Cybrdeck Lead
2026-12-01 | Tue | WK 09 | Sprint 5: Front-End UI Integration & Vercel Deployment | Protected Build & Engineering Execution | 5-7 hrs deep work: Construct UI components, state management & reactive query hooks. | Founders / Cybrdeck Lead
2026-12-02 | Wed | WK 09 | Sprint 5: Front-End UI Integration & Vercel Deployment | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Address hydration errors & frontend state syncing. | Mamba Program Lead
2026-12-03 | Thu | WK 09 | Sprint 5: Front-End UI Integration & Vercel Deployment | Validation, Testing & Integrations | 5-7 hrs build time: Polish error toasts, loading skeletons & optimistic updates. | Founders / Cybrdeck Lead
2026-12-04 | Fri | WK 09 | Sprint 5: Front-End UI Integration & Vercel Deployment | Deliverable Push & Weekly Codebase Review | Weekly codebase review & push: Deploy preview branch to Vercel and review user flows. | Founders / Cybrdeck Lead
2026-12-07 | Mon | WK 10 | Sprint 5: QA, Bug Squashing & Clickable Beta Release | Sprint Planning & Architecture Setup | 4-6 hrs build time + Sprint Planning: QA & UAT, squash critical bugs across all views. | Founders / Cybrdeck Lead
2026-12-08 | Tue | WK 10 | Sprint 5: QA, Bug Squashing & Clickable Beta Release | Protected Build & Engineering Execution | 5-7 hrs deep work: Resolve high-severity tickets, cross-browser quirks & UI glitches. | Founders / Cybrdeck Lead
2026-12-09 | Wed | WK 10 | Sprint 5: QA, Bug Squashing & Clickable Beta Release | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Review edge-case bug fixes with Program Lead. | Mamba Program Lead
2026-12-10 | Thu | WK 10 | Sprint 5: QA, Bug Squashing & Clickable Beta Release | Validation, Testing & Integrations | 5-7 hrs build time: Conduct end-to-end user acceptance tests and regression verification. | Founders / Cybrdeck Lead
2026-12-11 | Fri | WK 10 | Sprint 5: QA, Bug Squashing & Clickable Beta Release | Deliverable Push & Weekly Codebase Review | 60-90 min Sprint Review: Deliver Clickable Beta v1 demo and user feedback log. | Founders / Cybrdeck Lead | Clickable Beta v1
2026-12-14 | Mon | WK 11 | Sprint 6: Cybersecurity Validation & System Hardening | Sprint Planning & Architecture Setup | 4-6 hrs build time + Security Setup: Basic C-Sec validation, package audits & vulnerability scan. | Founders / Cybrdeck Lead
2026-12-15 | Tue | WK 11 | Sprint 6: Cybersecurity Validation & System Hardening | Protected Build & Engineering Execution | 5-7 hrs deep work: Configure CSP headers, sanitize user inputs & audit secret exposures. | Founders / Cybrdeck Lead
2026-12-16 | Wed | WK 11 | Sprint 6: Cybersecurity Validation & System Hardening | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Resolve penetration test findings & security alerts. | Mamba Program Lead
2026-12-17 | Thu | WK 11 | Sprint 6: Cybersecurity Validation & System Hardening | Validation, Testing & Integrations | 5-7 hrs build time: Verify production SSL, API rate limiting & DDoS basic protection. | Founders / Cybrdeck Lead
2026-12-18 | Fri | WK 11 | Sprint 6: Cybersecurity Validation & System Hardening | Deliverable Push & Weekly Codebase Review | Weekly codebase review & push: Audit security checklist and sign off on system hardening. | Founders / Cybrdeck Lead
2026-12-21 | Mon | WK 12 | Sprint 6: Billing Migration, Admin Handoff & Launch | Sprint Planning & Architecture Setup | 4-6 hrs build time + Ops Setup: Billing migration trigger, hand over admin credentials. | Founders / Cybrdeck Lead
2026-12-22 | Tue | WK 12 | Sprint 6: Billing Migration, Admin Handoff & Launch | Protected Build & Engineering Execution | 5-7 hrs deep work: Rotate production credentials, migrate live Stripe accounts & domain DNS. | Founders / Cybrdeck Lead
2026-12-23 | Wed | WK 12 | Sprint 6: Billing Migration, Admin Handoff & Launch | Program Lead Office Hours (The Anchor) - Technical Unblocking | 1 hr Office Hours (technical unblocking) + 4-5 hrs build: Verify environment switches & live payment flows. | Mamba Program Lead
2026-12-24 | Thu | WK 12 | Sprint 6: Billing Migration, Admin Handoff & Launch | Validation, Testing & Integrations | 5-7 hrs build time: Run final end-to-end smoke test on production deployment. | Founders / Cybrdeck Lead
2026-12-25 | Fri | WK 12 | Sprint 6: Billing Migration, Admin Handoff & Launch | Deliverable Push & Weekly Codebase Review | Formal Handoff & Wrap-up: Codebase handoff, archive developer sandbox & grant repo ownership. | Founders / Cybrdeck Lead | Codebase handoff

## Cohort Governance & Gate Ledger
SECTION 1: COHORT GOVERNANCE & FORMAL GATE LEDGER
Sprint / Week | Gate Name | Target Date | Gate Criteria (The Rule) | Founder Sign-Off / Status | SOW Link / Notes
Wk 02 | Technical SOW Lock | 2026-10-16 | Explicit MVP scope locked. Custom ML/extra integrations pushed to post-cohort. | [ Pending / Signed ] | Link to signed agreement
Wk 03 | Data Schema Approval | 2026-10-23 | Supabase/DB entity model approved. No schema changes allowed after this date without fee. | [ Pending / Approved ] | Link to ERD diagram
Wk 04 | Sandbox 15-Min Demo | 2026-10-30 | Founder logs into VPC sandbox & confirms environment access. | [ Pending / Verified ] | Sandbox URL
Wk 06 | API & Auth Staging Gate | 2026-11-13 | Founder supplies all 3rd-party keys (OpenAI, Stripe, etc.); test auth confirmed. | [ Pending / Verified ] | Key delivery checklist
Wk 08 | Strict Feature Freeze | 2026-11-27 | Final UI mockups locked. Zero new feature requests accepted past this date. | [ Hard Lock ] | Mockup freeze sign-off
Wk 10 | Beta v1 UAT Gate | 2026-12-11 | Only critical/blocking crash bugs accepted. Cosmetic/new feature requests deferred. | [ UAT Passed ] | UAT bug tracker
Wk 11 | C-Sec Launch Clearance | 2026-12-18 | Security scoping clear. Founder acknowledges data liability per MOU. | [ Cleared ] | Security audit notes
Wk 12 | Production & Billing Handover | 2026-12-25 | Founder enters credit card for AWS/Vercel/Supabase. Codebase transfer complete. Cybrdeck offboards. | [ Transferred ] | Billing transfer receipt
SECTION 2: FOUNDER KEY & ASSET DEPENDENCY TRACKER
Sprint / Week | Dependency / Asset Name | Target Due Date | Technical Specification & Security Scope | Founder Delivery Status | Access / Verification Link
Wk 02 | GitHub Org Access & Repository Transfer | 2026-10-16 | Org admin access granted to Cybrdeck team; base repository permissions provisioned. | [ Pending / Verified ] | GitHub org invite link
Wk 03 | Supabase DB Instance & Cloud Service Role | 2026-10-23 | Dedicated staging DB instance created; connection URL & service role credentials staged. | [ Pending / Approved ] | Supabase settings console
Wk 04 | Domain Registrar & DNS Delegation | 2026-10-30 | Cloudflare DNS management access delegated; staging and production CNAME records verified. | [ Pending / Verified ] | Cloudflare DNS dashboard
Wk 05 | OAuth 2.0 & Social Auth Client Keys | 2026-11-06 | Google Workspace & Apple Developer OAuth Client ID and secrets provisioned for auth flow. | [ Pending / Staged ] | Auth provider credentials
Wk 06 | AI / LLM API Production Keys (OpenAI/Anthropic) | 2026-11-13 | Tier-4 funded production API keys supplied; organization rate limits & spend caps verified. | [ Pending / Staged ] | API key delivery checklist
Wk 06 | Stripe Payment Gateway & Webhook Secrets | 2026-11-13 | Stripe live & test publishable/secret API keys generated; webhook endpoints configured. | [ Pending / Staged ] | Stripe developer console
Wk 07 | Transactional Email & Messaging (Resend/SendGrid) | 2026-11-20 | Domain DKIM/SPF DNS records authenticated; transactional API keys generated. | [ Pending / Staged ] | Email service verification
SECTION 3: OUT-OF-SCOPE & PHASE 2 FEATURE PIPELINE
Request ID | Feature Request / Idea Name | Logged Date | Technical Assessment & SOW Impact | Governance Disposition | Roadmap Target / Backlog Link
FEAT-01 | Multi-Tenant White-Labeling & Custom Subdomains | 2026-10-18 | Requires dedicated routing layer & tenant data isolation; excluded from MVP core. | [ Phase 2 Roadmap ] | Linear #ENG-104
FEAT-02 | Custom Fine-Tuned LLM Pipeline & LoRA Adapters | 2026-10-24 | Exceeds MVP compute budget; base prompt engineering & few-shot chaining fulfills specs. | [ Deferred to Post-Launch ] | Architecture RFC #03
FEAT-03 | Native Mobile Apps (iOS & Android / React Native) | 2026-11-02 | SOW explicitly locks scope to responsive web application (PWA); native builds deferred. | [ Phase 2 Roadmap ] | Mobile PRD draft
FEAT-04 | Enterprise SAML / Okta SSO Integration | 2026-11-08 | High implementation complexity; available as studio post-MVP add-on package. | [ Scope Add-On (Fee) ] | Add-On Quote #SOW-A1
FEAT-05 | Real-Time Collaborative Multi-User Editing | 2026-11-15 | Complex CRDT state sync; optimistic locking and standard polling satisfies MVP use case. | [ Phase 2 Roadmap ] | Backlog #UX-88
FEAT-06 | Automated PDF Report Generator & Vector Export | 2026-11-22 | Server-side headless browser rendering deferred; standard CSV and JSON export provided. | [ Phase 2 Roadmap ] | Linear #ENG-142